## Slide 1
18 January 2017
1
(Increasing Resilience of Cultural heritage: a supporting decision tool for the safeguarding of cultural assets)

## Slide 2
18 January 2017
2
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES
FOLLOW UP
SiTI - Istituto Superiore sui Sistemi Territoriali per l'Innovazione (coordinator)
CORILA – Consortium for managing research activities in the Venice Lagoon system
POLITO – Politecnico di Torino
TUB – Technische Universität Berlin
UNISDR – The United Nations Office for Disaster Risk Reduction
SDIS 04 – Service Départemental d’Incendie et de Secours des Alpes de Haute-Provence
MAJOR EVENTS
(hypothesis)

## Slide 3
18 January 2017
3
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES
FOLLOW UP
CH protection and management entities
Research
centres
Governmental Authorities
Emergency operators
Citizens & local communities
PROJECT’S DURATION: 18 months
TOTAL COST:
791,893 €
EC co-financing: 593.913,83 €
MAJOR EVENTS
(hypothesis)

## Slide 4
18 January 2017
4
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES
FOLLOW UP
Natural Disasters
Manmade Threats
Art pieces as:
Witnesses of people’s history
Religious symbols
Material catalysts of culture
Universal value and heritage of Mankind
High market value
Investment assets
Earthquakes
Floodings
Fires
Extreme conditions
Vandalism
Armed Conflicts
Illegal trade
Terrorism
Theft / Looting
Counterfeit
A growing need for security in cultural heritage domain, which are constantly threatened
MAJOR EVENTS
(hypothesis)
“Historia testis temporum, lux veritatis, vita memoriae, magistra vitae, nuntia vetustatis.”
“History is the witness that testifies to the passing of time; it illumines reality, vitalizes memory, provides guidance in daily life and brings us tidings of antiquity.”
Cicerone

## Slide 5
18 January 2017
5
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES
FOLLOW UP
Pilot and demonstration project with replication capacity focusing on urban resilience to disasters.
Aiming at enhancing the capability of Civil Protection (CP) to prevent/mitigate disasters impacts on Cultural Heritage (CH).
Tool to understand the risk of CH to be damaged.
Disaster risk reduction strategy (for prevention and resilience).
European Heritage Map
Cadaster
Risk scenarios monitoring platform
Advice-seeking interface
Crowd-data acquiring from citizens and stakeholders
3D and virtual reality models
Base for training, education and research
European Interoperable Database (EID) for CH, a unique framework.
MAJOR EVENTS
(hypothesis)
OUTPUT

## Slide 6
18 January 2017
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES
FOLLOW UP
6
TASK 0
TASK 1
TASK 2
TASK 3
TASK 4
MANAGEMENT
ANALYSIS OF REQUIREMENTSTASK
EID TESTING AND PILOT CASES
DATABASE DESIGN & IMPLEMENTATION
COMMUNICATION AND DISSEMINATION
MAJOR EVENTS
(hypothesis)

## Slide 7
18 January 2017
7
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES (1/1)
FOLLOW UP
MAJOR EVENTS
(hypothesis)
A 0.1 D 0.1
A.0.2 D.0.2
A 0.3 D 0.3
A 0.3 D 0.4
A 0.3 D 0.4
A 1.1
A 1.2 D.1.1
A 1.3
A 1.4
A 1.5 D.1.2
A 1.6 D.1.3
A 2.1
A 2.2 D.2.1
A 2.3
A 2.5
D 2.2
A 2.6 D 2.3
A 27 D 2.4
A 2.8
A 2.9 D 2.5
0. MANAGEMENT
3. EID TESTING AND PILOT CASES
A 3.1
A 3.2 D.3.1
A 3.3
A 3.4
D 3.2
A 3.5
A 3.6 D 3.3
A 4.1 D 4.1
A 4.2 D 4.2
A 4.2 D 4.2
A 4.3 D 4.3
A 4.4 D 4.4
A 4.5 D 4.5
SITI
SDIS 04
POLITO
CORILA
TUB
Partner Leader
1. ANALYSIS OF REQUIREMENTS
4. COMMUNICATION AND DISSEMINATION
2. DATABASE DESIGN & IMPLEMENTATION

## Slide 8
18 January 2017
8
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES (1/2)
FOLLOW UP
MAJOR EVENTS
(hypothesis)

## Slide 9
18 January 2017
9
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES
FOLLOW UP
MAJOR EVENTS
(hypothesis)

## Slide 10
18 January 2017
10
PARTNERS and
AREA OF ACTIVITY
BENEFICIARIES,
COST and DURATION
WHY THE PROJECT IS
NECESSARY
OBJECTIVES
WORK PLAN
DELIVERABLES and DEADLINES
FOLLOW UP
the automatic translation of existing cultural heritage inventories and databases
highlight further requirements from disaster risk management planning stakeholders
the project
will raise awareness
on CH protection needs in Europe, fostering investments and interests by private/public stakeholders.
the translation of the system to Linked Open Data (LOD)
other kinds of modelling and analysis algorithms
the inclusion of the management of further kinds of disasters in the database and risk analysis algorithms
MAJOR EVENTS
(hypothesis)

## Slide 11
Sergio Olivero
Head of Security and Business Models for Energy Networks and Infrastructures
SiTI – Higher Institute on Territorial Systems for Innovation
Via Pier Carlo Boggio 61
10138 Torino
Italy
Tel +39 011 1975 1111
Mobile: +39 335 12 73 521
Email: olivero@siti.polito.it
Massimo Migliorini
Email: migliorini@siti.polito.it
www.siti.polito.it
Thank you
18 January 2017
11